## Sheet2
Requirements Catalogue |  |  |  |  | Project: | Pitman CRM
[5 empty] | Author: | Samantha Richards
[5 empty] | Date: | 2025-11-22
Test Result
ID | Epic | Description/User Story (As a_____ I want_____ So that _____) | Source | Priority (MoSCoW) | Acceptance Criteria | Comments | Related Documents | Related Requirements | Accept | Reject
1.1 | Accounts & Contact Management | As a sales person, I want to be able to organise Pitman contacts effectively, so that I can maximise the value per customer. | Sales Person | Must Have | The solution will organise contacts in alphabetical order A-Z by first name.
The solution offers hierarchy in account management by linking related accounts with their parent account.
It enables viewing child account information directly from the parent account page, thus helping to identify cross-selling and upselling opportunities.
The solution allows us to view the customers email address.
1.2 | Accounts & Contact Management | As a sales person, I want to create and update contact records so that I can keep an accurate view of each customer's account and enrolment status. | Sales Person | Must Have | When I save the contact, then a unique contact record is created and visible in the contact list.
when I create a new contact, I can enter name, email, phone, address and billing details.
When I edit an existing contact and save, then the updated details are stored and visible immediately
1.3 | Accounts & Contact Management | As a Marketing User, I want to segment contacts by attributes so that I can target email campaigns effectively. | Marketing | Must Have | I can view and filter contacts by at least course interest, location and lead status.
can save a filter/segment and re-use it when creating a campaign.
Only contacts matching the selected filters are pulled into the campaign audience.
1.4 | Accounts & Contact Management | As a Manager, I want to see a full interaction history for each contact so that I can resolve issues and understand the customer journey. | Manager | Must Have | I can see a timeline of key interactions (emails sent, calls logged, notes, enrolments).
Each interaction shows date/time, user, and type of activity.
I can add a note to an interaction and it is saved against the contact.
2.1 | Lead Management | As a sales person, I want web enquiries to automatically create leads in the CRM so that I can follow up quickly and not miss potential students. | Sales Person | Must Have | When a prospect submits the website form, a new lead record is created in the CRM.
The lead contains the prospect’s details and course of interest from the form.
The lead is given a default status (e.g. “New”) and appears in my lead list
2.2 | Lead Management | As a marketing user, I want to track which campaign each lead came from so that I can measure marketing ROI. | Marketing | Must Have | Each new lead has a “Source” field (e.g. Google Ads, Email Campaign X, Organic).
When a lead originates from a tracked campaign, the Source is populated automatically.
I can run a report or view that groups leads by Source.
2.3 | Lead Management | As a Manager, I want to assign and reassign leads to sales users so that workload is balanced and every lead has an owner. | Manager | Must Have | I can view a list of unassigned leads.
I can assign a lead to a specific sales user.
The assigned user can see those leads in their own pipeline.
I can reassign a lead to another sales user if needed.
3.1 | Dashboard & Reporting | As a Manager, I want a high-level dashboard of leads, conversions and revenue so that I can track performance against targets. | Manager | Must Have | The dashboard shows number of new leads, number of enrolments, and revenue for a selected period.
I can filter the dashboard by date range.
Figures update automatically as new leads and enrolments are added.
3.2 | Dashboard & Reporting | As a sales person, I want a personal dashboard showing my open leads and follow-up tasks so that I can prioritise my work. | Sales Person | Must Have | The dashboard shows my total open leads and leads by status (e.g. New, In Progress, Won, Lost).
I can see a list of my upcoming follow-up tasks with due dates.
Clicking a lead or task takes me to the relevant record.
3.3 | Dashboard & Reporting | As a Marketing User, I want reports on email performance (opens, clicks, unsubscribes) so that I can improve future campaigns. | Marketing | Must Have | For each campaign, I can see total sent, delivered, opened, clicked, unsubscribed.
I can export campaign performance data to CSV/Excel.
I can filter results by date range or campaign.